{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":30,"n_cols":15,"rows_kept":30,"merged":[[0,0,0,14],[29,0,29,14]],"flags":["formulas_cached_only"]}
["惠州市城市黑臭水体治理清单"]
["序号","城市","区","黑臭水体名称","水体类别（河、湖、塘、涌）","治理前黑臭等级（轻度、重度）","黑臭水体\n面积（km^2）","黑臭长度 \n（km）","治理工程开工时间","治理工程完成时间（主体工程）","初见成效\n目标时间","长制久清\n目标时间","河湖长\n姓名","所在单位\n名称","职务"]
[1,"惠州市","惠城区","河桥水","河流","轻度黑臭",0.03,{"v":3,"d":"3.00"},"2016年5月","2019年9月","2020年4月","2020年12月","钟阳光","惠城区政府","副区长"]
[2,"惠州市","惠城区","望江沥","河流","轻度黑臭",0.0795,{"v":5.3,"d":"5.30"},"2015年5月","2019年6月","2020年1月","2020年12月","钟文宇","惠城区委","区委常委、统战部部长"]
[3,"惠州市","惠城区","梅湖沥","河流","重度黑臭","0.004",{"v":0.8,"d":"0.80"},"2016年8月","2019年6月","2020年1月","2020年12月","黄智勇","惠城区委","区委常委、区委办公室主任"]
[4,"惠州市","惠城区","新民排渠","河流","轻度黑臭","0.135",{"v":9,"d":"9.00"},"2016-03-01","2019年9月","2020年4月","2020年12月","陈广文","惠城区政府","副区长"]
[5,"惠州市","惠城区","洛塘渠","河流","重度黑臭","0.162",{"v":8.1,"d":"8.10"},"2016-03-01","2019-06-01","2020年1月","2020年12月","黄智勇","惠城区委","区委常委、区委办公室主任"]
[6,"惠州市","惠城区","大湖溪沥","河流","轻度黑臭","1.055",{"v":21.1,"d":"21.10"},"2016年12月","2019年9月","2020年4月","2020年12月","陈广文","惠城区政府","副区长"]
[7,"惠州市","惠城区","陈塘河","河流","轻度黑臭","0.336",{"v":11.2,"d":"11.20"},"2016年4月","2019年9月","2020年4月","2020年12月","钟阳光","惠城区政府","副区长"]
[8,"惠州市","惠城区","莲塘沥","河流","重度黑臭","0.0266",{"v":3.8,"d":"3.80"},"2016年4月","2019年9月","2020年4月","2020年12月","钟文宇","惠城区委","区委常委、统战部部长"]
[9,"惠州市","惠城区","冷水坑水","河流","轻度黑臭","0.026",{"v":2.6,"d":"2.60"},"2016年5月","2020年3月","2020年10月","2021年9月","钟阳光","惠城区政府","副区长"]
[10,"惠州市","惠城区","木沥河","河流","轻度黑臭","0.1125",{"v":7.5,"d":"7.50"},"2016年8月","2019年3月","2019年10月","2020年12月","张向城","惠城区政府","副区长"]
[11,"惠州市","惠城区","沙墩头沥","河流","重度黑臭","0.0176",{"v":2.2,"d":"2.20"},"2016年8月","2017年9月","2019年9月","2020年12月","费霞","惠城区政府","副区长"]
[12,"惠州市","惠城区","高屈沥","河流","轻度黑臭","0.0328",{"v":4.1,"d":"4.10"},"2016年3月","2019年9月","2020年4月","2020年12月","叶淑斌","惠城区委","区委常委、组织部部长"]
[13,"惠州市","惠阳区","古屋水","河流","轻度黑臭",27.31,6.66,"2016-12-01","2019-09-01","2020-04-01","2020-12-01","谭星海","惠阳区委、区政府","区委常委、常务副区长"]
[14,"惠州市","惠阳区","横岭水","河流","轻度黑臭",138.42,8.76,"2016-12-01","2019-09-01","2020-04-01","2020-12-01","闫健平","惠阳区人民政府","副区长"]
[15,"惠州市","大亚湾区","妈庙河","河流","轻度黑臭",0.01608,2.01,"2016-10-01","2019-06-01","2019-12-01","2020-12-01","黄伟忠","大亚湾开发区委、区管委会","区委常委、区管委会副主任"]
[16,"惠州市","大亚湾区","响水河","河流","轻度黑臭",{"v":0.0402,"d":"0.04020"},8.04,"2015-08-01","2019-06-01","2019-12-01","2020-12-01","潘添新","大亚湾开发区管委会"," 区管委会副主任"]
[17,"惠州市","仲恺区","陈江河干流\n（特育桥至五一桥）","河流","重度黑臭",{"v":0.096,"d":"0.10"},{"v":4.8,"d":"4.80"},"2016-09-01","2019-09-01","2020-04-01","2020-12-01","刘勇辉","仲恺区管委会","副主任"]
[18,"惠州市","仲恺区","肋下河干流（惠河高速桥下至梅光村与甲子河汇合口）","河流","轻度黑臭",{"v":0.0432,"d":"0.04"},2.16,"2014-09-01","2019-09-01","2020-04-01","2020-12-01","刘子尧","仲恺区委、区管委会","区委常委、区管委会副主任"]
[19,"惠州市","仲恺区","水围河干流及支流（惠阳交界断面至平塘汇入口）","河流","轻度黑臭",{"v":0.27036,"d":"0.27"},15.02,"2016-09-01","2019-09-01","2020-04-01","2020-12-01","王云波","仲恺区委","区委常委"]
[20,"惠州市","仲恺区","南塘河干流及支流（罗布群水库至甲子河汇入口）","河流","重度黑臭",{"v":0.05472,"d":"0.05"},6.84,"2016-09-01","2020-09-01","2021-04-01","2021-12-01","陈智明","仲恺区委","区委常委"]
[21,"惠州市","仲恺区","甲子河（惠河高速桥下至甲子桥）","河流","轻度黑臭",{"v":0.077,"d":"0.08"},{"v":3.5,"d":"3.50"},"2014-09-01","2019-09-01","2020-04-01","2020-12-01","闫维","仲恺区委","区委常委、纪委书记"]
[22,"惠州市","仲恺区","梧村河（梧村水库至平塘入口）","河流","轻度黑臭",{"v":0.2432,"d":"0.24"},{"v":6.4,"d":"6.40"},"2016-09-01","2019-09-01","2020-04-01","2020-12-01","林瑞明","仲恺区管委会","区管委会副主任"]
[23,"惠州市","仲恺区","马过渡河干流（惠盐高速桥下至惠河高速桥下）","河流","轻度黑臭",{"v":0.0792,"d":"0.08"},{"v":3.6,"d":"3.60"},"2016-09-01","2019-09-01","2020-04-01","2020-12-01","李尊友","仲恺区管委会","区管委会副主任"]
[24,"惠州市","仲恺区","西坑河（西坑村起至镇隆池禾尾汇合）","河流","轻度黑臭",{"v":0.0132,"d":"0.01"},1.32,"2016-09-01","2019-09-01","2020-04-01","2020-12-01","李尊友","仲恺区管委会","区管委会副主任"]
[25,"惠州市","仲恺区","甲子河（甲子桥至金竹水闸）","河流","轻度黑臭",{"v":0.12375,"d":"0.12"},4.95,"2016-12-01","2019-09-01","2020-04-01","2020-12-01","徐颂","仲恺区委","区委常委"]
[26,"惠州市","仲恺区","金星河（金星村至学溪桥）","河流","重度黑臭",{"v":0.04425,"d":"0.04"},2.95,"2016-09-01","2019-09-01","2020-04-01","2020-12-01","扈伟","仲恺区管委会","副主任"]
[27,"惠州市","仲恺区","甲子河潼侨金竹水闸2条支流","河流","重度黑臭",{"v":0.02864,"d":"0.03"},3.58,"2016-12-01","2019-09-01","2020-04-01","2020-12-01","徐颂","仲恺区委","区委常委"]
["注：\n    1.治理清单实行动态管理，各地须对新发现的黑臭水体一并纳入治理清单。\n    2.对于新发现的黑臭书体，各地须立即制定相应的实施方案开展整治工作。\n    3.各地必须遵守“发现一条，整治一条”的原则。中央环保督察和国家及省级黑臭水体整治环境保护专项行动确认的黑臭水体须一并纳入治理清单。"]