{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":11,"n_cols":5,"rows_kept":11,"merged":[[0,0,0,4],[3,1,8,1]],"flags":["formulas_cached_only"]}
["惠州市交通运输局2022年\n在建铁路项目、铁路沿线安全隐患整治监督“双随机一公开”检查结果"]
["序号","对象类型","抽查对象","抽查日期","检查情况"]
[1,"在建铁路项目","莞惠城际小金口至惠州北段DK0+025～DK5+050段","2022.2.22","1.右线明挖隧道端头挡墙脚手架内侧未设置剪刀撑；\n2.工人生活区存在违规接插排现象；             \n3.现场空压机压力表4个未进行标定，无日常检查记录；\n4.安全生产管理办法应补充应急演练制度；\n5.安全教育台账人员汇总表中的人员与签字表人员数量不对应，表中司索工与普工同一期进行安全教育，不符合要求。                  "]
[2,"铁路沿线安全隐患整治督查","博罗县","2022.03.10","未发现问题"]
[3,null,"仲恺高新区","2022.04.27","未发现问题"]
[4,null,"仲恺高新区","2022.08.09","赣深铁路阿公石二号隧道出口处防洪安全隐患整治施工进度缓慢，要求下来加快施工进度，尽早完成验收。"]
[5,null,"惠城区","2022.08.23","红花湖景区范围内京九线K2268+074隐患点，涵洞内淤泥堆积，护坡未完成挂网喷浆加固。"]
[6,null,"仲恺高新区","2022.08.24","赣深铁路阿公石二号隧道出口现场截水沟畅通完好、无堵塞，但山体边坡加固工作目前仍未完成。"]
[7,null,"惠城区","2022.12.16","红花湖景区范围内京九线K2268+074隐患点，现场已完成整治，排水基本畅通，下来待铁路部门实地确认无问题后开展销号验收工作。"]
[8,"在建铁路项目","广汕铁路GSSG12标惠城南车站","2022.10.28","1.施工现场安全警示标语宣传不到位，设置不足。\n2.现场焊工无证作业\n3.电焊机外壳未接PE线。"]
[" "]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}